## Cover Page
Smart Shop
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Diptendu Sil
| Role | Associate
Signature
Date
Project ID: Car Servicing | <BGL19IJ004/20> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <Smart Shop> Project ID: <BGL19IJ004/20> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1 | 1.1 | Create Homepage with User SignUp link | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 1 | 1.2 | Redirection to User SignUp | Diptendu | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2 | 2.1 | Create User registration form | Diptendu | 2 | 0 | 0 |  | 0 | 0 | 0 | Completed
FEA 3 | 3.1 | Adding validations to each field. | Diptendu | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 3 | 3.2 | Create database schema for User | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 3 | 3.3 | Create Spring controller for user management | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 3 | 3.4 | Create angular service for user handling | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 3 | 3.5 | Integrate angular with Spring | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 3 | 3.6 | Saving user information into database through UI | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 4 | 4.1 | Create login link and redirection to login page | Diptendu | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 4 | 4.2 | Create Login form and adding validations | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0
FEA 4 | 4.3 | Create authentication service in Spring | Diptendu | 3 | 0 | 0 | 0 | 0 | 0 | 0
FEA 5 | 4.4 | Integrate login UI with Spring authentication with validations message | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 8 | 8.1 | Create redirection to Admin dashboard on login | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 8 | 8.2 | Create Admin dashbard UI with create Shop manager link | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 8 | 8.3 | Create Shop manager creation form | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 9 | 9.1 | Validation of shop manager creation form | Diptendu | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 10 | 10.1 | Integrate angular with Spring for manager creation | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 |  | Completed
FEA 11 | 11.1 | Create shop manager redirection on successful login and invalid message on failure | Diptendu | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 12 | 12.1 | Create Shop manager Dashboard UI | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 12 | 12.2 | Create Product microservice | Diptendu | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 12 | 12.3 | Create database schema for Products | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 12 | 12.4 | Create Product controller in Spring for adding / retrieving / modifying / deleting products | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 12 | 12.5 | Create UI to display all products and integrate with Spring | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 13 | 13.1 | Create UI to display product updation form and form validations | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 13 | 13.2 | Integrate with Spring to update a specific product on successful validation or else display error message on failure | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 14 | 14.1 | Create UI to display product addition form and form validations | Diptendu | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 14 | 14.2 | Integrate with Spring to add a product on successful validation or else display error message on failure | Diptendu | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
|  | Total |  | 40.5 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
complete planned things for sprint 1

## Sprint 2
Sprint Backlog <Smart Shop> Project ID: <BGL19IJ004/20> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 6 | 6.1 | Redirect to user dashboard on successful login | Diptendu | 1 | [6 empty] | Completed
FEA 6 | 6.2 | Create a search bar in User dashboard to handle user input | Diptendu | 1 | [6 empty] | Completed
FEA 6 | 6.3 | Create a search controller in Product service to provide search results | Diptendu | 2 | [6 empty] | Completed
FEA 6 | 6.4 | Display Search results retrieved from backend | Diptendu | 1 | [6 empty] | Completed
FEA 7 | 7.1 | Create Product details UI to display product details | Diptendu | 1 | [6 empty] | Completed
FEA 7 | 7.2 | Integrate Product details UI with Spring to display product details | Diptendu | 2 | [6 empty] | Completed
FEA 15 | 15.1 | Create UI to Generate New Bill | Diptendu | 3 | [6 empty] | Completed
FEA 15 | 15.2 | Create Billing Microservice in Spring | Diptendu | 2 | [6 empty] | Completed
FEA 15 | 15.3 | Create Billing Schema in Database | Diptendu | 2 | [6 empty] | Completed
FEA 15 | 15.4 | Create Billing Controller in microservice | Diptendu | 2 | [6 empty] | Completed
FEA 15 | 15.5 | Add validations to New Bill form and connect to Spring. | Diptendu | 1 | [6 empty] | Completed
FEA 15 | 15.6 | On successful validation add the bill to database and update stocks | Diptendu | 1 | [6 empty] | Completed
FEA 16 | 16.1 | Add purchase to Customer's purchase history | Diptendu | 1 | [6 empty] | Completed
FEA 17 | 17.1 | Create UI to update Aisle and Shelf Details of a product | Diptendu | 1 | [6 empty] | Completed
FEA 17 | 17.2 | Save updated details in database | Diptendu | 1 | [6 empty] | Completed
FEA 18 | 18.1 | Create Offers schema in database | Diptendu | 2 | [6 empty] | Completed
FEA 18 | 18.2 | Create Offfers controller in spring to add / retrieve / modify / delete offers | Diptendu | 2 | [6 empty] | Completed
FEA 18 | 18.3 | Create UI to Flash offers for current day | Diptendu | 1 | [6 empty] | Completed
FEA 18 | 18.4 | Integrate UI to Spring to display offers from database | Diptendu | 1 | [6 empty] | Completed
FEA 19 | 19.1 | Create UI for Offer updation and add validations | Diptendu | 1 | [6 empty] | Completed
FEA 19 | 19.2 | On successful validation update offer in database. | Diptendu | 1 | [6 empty] | Completed
FEA 20 | 20.1 | Create Schema for Reward Points | Diptendu | 2 | [6 empty] | Completed
FEA 20 | 20.2 | Create Controller to add / modify reward | Diptendu | 2 | [6 empty] | Completed
FEA 20 | 20.3 | Create UI in New Bill to display reward points earned in that bill | Diptendu | 1 | [6 empty] | Completed
FEA 21 | 21.1 | Create UI in New Bill to display reward points of user and option to redeem. | Diptendu | 1 | [6 empty] | Completed
FEA 21 | 21.2 | Integrate it to backend and update reward point on successful billing. | Diptendu | 0.5 | [6 empty] | Completed
FEA 22 | 22.1 | Create UI to display new Products and integrate with Spring | Diptendu | 0.5 | [6 empty] | Completed
FEA 23 | 23.1 | Create UI to display purchase history of a customer | Diptendu | 0.5 | [6 empty] | Completed
FEA 23 | 23.2 | Integrate with Spring to display purchase details of customer | Diptendu | 0.5 | [6 empty] | Completed
FEA 24 | 24.1 | Create controller that returns recommendation for a particular user. | Diptendu | 1 | [6 empty] | Completed
FEA 24 | 24.2 | Create UI to display recommendations and integrate with Spring | Diptendu | 0.5 | [6 empty] | Completed
FEA 25 | 25.1 | Create a link in navigation to log off user | Diptendu | 0.5 | [6 empty] | Completed
FEA 26 | 26.1 | Create UI to take secret answers of user and validate them and redirect to reset password page on success | Diptendu | 1 | [6 empty] | Completed
FEA 26 | 26.2 | Create UI to reset password and update password in database on successful validation. | Diptendu | 1 | [6 empty] | Completed
|  | Total |  | 42 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
complete the critical requirements

## Data (hidden)
In-Progress
Completed
N/A