## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Project ID: Car Servicing | <Batch code/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <E-learning management> Project ID: <Batch code/132> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1.2 | 1.2 003 | Registration for Vendor | Kunal | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 004 | Validation for pages | Kunal,Vikrat | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 005 | Connection Establishment | Utkarsh | 2 | 2 | 2 |  | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 006 | Creation of BO and DAO classes for FEA1 and 2 | Utkarsh,Nitesh | 4 | 4 | 4 | 2 | 2 | 0 | 0 | Completed
FEA 1.2 | 1.2 007 | Login Servlet | Nitesh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 008 | Creation of Signup Servlet | Utkarsh | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 009 | UI for User Home | maneesh,vikrant | 2 | 2 | 1 | 1 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 010 | UI to edit User Profile | Kunal | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Completed
FEA 1.2 | 1.2 011 | UI for account security or deactivate account | Maneesh | 5 | 5 | 5 | 5 | 5 |  | 0 | Completed
FEA 1.3 | 1.3 001 | User Authentication for Users | Utkarsh | 3 | 3 | 2 | 1 | 0 | 0 | 0 | Completed
FEA 1.3 | 1.3_002 | user logout | maneesh | 2 | 2 | 2 | 2 | 2 |  | 0
0
FEA 0 | 1 | Documentation | Vikrant | 8 | 8 | 8 | 8 | 8 | 0 | 0 | Completed
FEA 2.2 | 2.2_001 | UI for user payment | kunal | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Completed
FEA 2.2 | 2.2_002 | ui testing of user home | vikrant | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Completed
FEA 2.2 | 2.2_003 | services ui user | kunal | 2 | 1 | 1 | 1 | 0 | 0 | 0 | Completed
FEA 2.2 | 2.2_004 | courses ui for user | kunal,vikrant | 2 | 2 | 2 | 2 | 2 | 2 | 1 | Completed
FEA 2.2 | 2.2_005 | ui for support in user | maneesh | 4 | 4 | 2 | 4 | 4 | 0 |  | Completed
FEA 2.2 | 2.2_006 | ui for user courses | kunal,vikrant | [6 empty] | 0 | Completed
FEA 2.2 | 2.2_007 | ui for user add/edit | kunal | 2 | 2 | 1 | 1 | 1 | 0 | 0 | Completed
FEA 2.2 | 2.2_008 | user payment backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Completed
FEA 2.2 | 2.2_009 | user courses backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Completed
FEA 2.2 | 2.2_010 | user my courses backend | utkarsh,nitesh | 2 | 2 | 1 | 1 | 1 | 1 | 0 | Completed
FEA 2.2 | 2.2_011 | user profile backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Completed
FEA 2.2 | 2.2_012 | user services backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Completed
FEA 2.2 | 2.2_013 | user payment backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Completed
FEA 2.2 | 2.2_014 | user add/edit backend | utkarsh,nitesh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Completed
FEA 2.2 | 2.2_015 | scripting | vikrant | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Completed
|  | Total |  | 56 | 55 | 46 | 36 | 32 | 7 | 1
Sprint Goal
complete planned things for sprint 1

## Sprint 2
Sprint Backlog <E-learning management> Project ID: <Batch code/132> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 0 | 1 | Sprint Planning for Sprint 2 | All Team members | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 0 | 2 | Behavioural session | All Team members | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_001 | vendor courses,services ui | vikrant | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_002 | vendor home ui,logout ui,profile ui | kunal,maneesh | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Completed
FEA 2.3 | 2.3_003 | vendor services_courses,notification,vendor courses_services | vikrant | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_004 | vendor add services | maneesh | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_005 | vendor course seggregation formwise | kunal | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_006 | database updation | utkarsh | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Completed
FEA 2.3 | 2.3_007 | vendor backend for course | utkarsh,nitesh | 2 | 2 | 1 | 1 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_008 | vendor backend for course service | utkarsh,nitesh | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Completed
FEA 2.3 | 2.3_009 | vendor backend profile | utkarsh,nitesh | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Completed
FEA 2.3 | 2.3_010 | vendor backend services | utkarsh,nitesh | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Completed
FEA 3.1 | 3.1_001 | listing service backend | utkarsh,nitesh | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Completed
FEA 3.2 | 3.2_001 | listing service backend | utkarsh,nitesh | 2 | 2 | 2 | 1 | 0 | 0 | 0 | Completed
FEA 0 | 3 | unit testing test cases pass/fail | vikrant | 2 | 2 | 2 | 1 | 1 | 1 | 0 | Completed
FEA 2.1 | 2.1_001 | add user list admin | vikrant,maneesh | 2 | 2 | 2 | 1 | 1 | 1 | 0 | Completed
FEA 2.1 | 2.1_002 | admin home | maneesh | 2 | 2 | 2 | 1 | 1 | 1 | 0 | Completed
FEA 2.1 | 2.1_003 | admin backend update/delete | utkarsh,nitesh,kunal | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Completed
FEA 2.1 | 2.1_004 | Scripting | maneesh,vikrant | 8 | 4 | 4 | 2 | 2 | 0 | 0 | Completed
FEA 0 | 4 | sprint backlog | vikrant | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Completed
FEA 2.2 | FEA 2.2_001 | user modifications | nitesh,utkarsh,kunal | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Completed
FEA 0 | 5 | documentation changes by tasneem | vikrant | 5 | 5 | 5 | 5 | 5 | 5 | 0 | Completed
|  | Total |  | 64 | 55 | 46 | 37 | 32 | 30 | 0
Sprint Goal
complete the critical requirements

## Data (hidden)
In-Progress
Completed
N/A